## All
Complete | Task | When to Initiate Task | Party Responsible | Task Description | Marketing | Date
| Select Program Chairperson | 1.5-2 years prior to meeting | AMS Board or Committee | *Program Chair is selected, appointed, or volunteers; (Selection usually takes place at previous conference during Board/Committee meeting)
| Select Program Committee | 1.5-2 years prior to meeting | Program Chair | *Program Chair selects those who will help organize the program
| Select Meeting Location (City, State) | 1.5-2 years prior to meeting | Program Chair, Program Committee, Committee Chair, Committee and AMS Staff | *Program chair and committee discuss and provide 3 ranked locations and dates for meeting *Program chair and committee discuss, possible dates, meeting space needs (short courses, exhibits) and events and communicate to AMS Staff *Based on dates, locations, and meeting space/event needs, AMS Staff prepares a Request for Proposal and circulates to Convention and Visitor's Bureau for each city as well as national sales contacts *AMS Staff gathers proposals, negotiates, and organizes venue options *AMS Staff sends Program Chair and Program Committee a Venue Summary based on proposals received *AMS Staff, Program Chair, and Program Committee select a final city location based on dates, room rates, facility availability etc.
| Select Meeting Location (Hotel/Dates) | 1-1.5 years prior to meeting | Program Chair and AMS Staff | *AMS Staff negotiates further with venues in chosen city location to receive best and final offers *AMS Staff conducts a site visit to meeting city to compare the venues that have bid on the meeting *AMS Staff and Program Chair discuss proposals and findings from site visit and select venue based on available dates, room rates, and room requirements *AMS staff negotiates and signs venue contract
| Discuss Program Chair Responsibilities and Deadlines/Submit Program Chair Funding Form | Upon contract signing | AMS Staff and Program Chair | *AMS Staff contacts Program Chair with Meeting Deadlines (THIS Document) and discusses tasks *AMS Staff directs Program Chair to the Meetings Section of the Chair & Member Information webpage in the STAC website for guidlines and forms. *AMS Staff explains availability/approval process for Program Chair Funds (Program Chair submits Form for approval by STAC Chair)
| Develop Marketing Plan | Upon contract signing | AMS Staff | *AMS Staff chooses a Meeting Image to be used on website and on social media (Program Chair/Committee is welcome to provide this image as well *AMS Staff puts together a list of past authors and meeting attendees to use for email marketing and maintains this list. *AMS Staff develops marketing plan (includes setting twitter hashtag and creating facebook event)
| Develop Meeting Theme | 1-1.5 years prior to meeting | Program Chair and Program Committee | *Program Chair and Committee develops a conference theme and/or special subject matter to incorporate into Call of Papers (if applicable) *If Program Chair and Committee would like to hold a special or named session, they should seek approval from the STAC Commissioner at this time
| Prepare Call for Papers | 1-1.5 years prior to meeting | Program Chair and Program Committee | *AMS Staff provides Program Chair with skeleton for Call for Papers *Program Chair develops Call for Papers (includes meeting theme, session and abstract topics, abstract deadlines, joint sessions, special/named sessions (if approved) and student awards from PCF (if approved)) and submits to AMS Staff for approval and circulation *Program Chair also develops topics that will be used on abstract submission website and will eventually serve as session titles during program organization
| Circulate Call for Papers/Save the Date Announcement | 1-1.5 years prior to meeting | AMS Staff | *AMS Staff makes first announcement regarding the meeing *Program Chair and Program Committee are welcome to advertise the meeting through any of their own channels as well | Social Media, Soundings, Email, BAMS
| Develop Meeting Budget | 1-1.5 years prior to meeting | AMS Staff | *AMS Staff develops budget for all aspects of the meeting based on past meetings' program and needs *Program chair should inform AMS Staff of any changes or updates for meeting needs
| Develop Exhibits Program | 1-1.5 years prior to meeting | AMS Staff, Program Chair, and Program Committee | *Develop exhibit program (if applicable) *Discuss and develop preliminary exhibit schedule *Program Committee to provide AMS Staff with list of possible exhibitors *AMS Staff develops floor plan *AMS Staff starts developing service manual and marketing plan
| Develop Short Course Program | 1-1.5 years prior to meeting | AMS Staff and Program Chair | *Develop short course (if applicable) *Program Chair reaches out to potential short course organizers *Short Course organizer submuts application for course to Board of Continuing Education for approval
| Develop Sponsorship Plan | 1-1.5 years prior to meeting | AMS Staff, and Program Chair | *AMS Staff discusses role of Program Chair and Lead Planner in securing sponsorship for the conference. *AMS Staff and Program Chair identify events/items that could be sponsored.
| Discuss Local Chapter Involvement | 1-1.5 years prior to meeting | AMS Staff and Program Chair | *AMS Staff and Program Chair discuss possibility of involving the Local AMS Chapter in the meeting *AMS Staff to contact Local Chapter President to consider collaboration if desired
| Discuss BECP Involvement | 1-1.5 years prior to meeting | AMS Staff and Program Chair | *AMS Staff and Program Chair discuss possibility of involving the AMS Board on Early Career Professionals *AMS Staff to contact BECP to consider collaboration if desired
| Reach Out to Potential Sponsors | 10-12 months prior to meeting | Program Chair | *AMS Staff provides Sponsorship Rate Sheet *Program Chair reaches out to potential and past sponsors
| Set Up AMS Student Travel Grant (not from PCF) | 10-12 months prior to meeting | AMS Staff | *AMS Meetings Staff provides AMS Development Staff meeting info for AMS Student Travel Grant (this is separate from any student awards/travel provided by Program Chair Funds) *AMS Development Staff opens application process for Student Travel Grants
| Develop Meeting Webpage and Open Abstract Submission Process | 10-12 months prior to meeting | AMS Staff and Program Chair | *AMS Staff develops and sets up Meeting Webpage on AMS website (Important Deadlines, Call for Papers, Abstract Submission Link, Student Opportunities (AMS Student Travel Grant, Volunteer Opportunities, Student Awards/Travel from PCF, other), Author/Presenter Information, Exhibits (if applicable)), Sponsorship Opportunities *Committee should add link to the meeting's webpage and social media info to their AMS Committee Webpage *AMS Staff opens online abstract submission process (using topics from Program Chair) *AMS Staff Emails past meeting authors and attendees soliciting abstract submissions | Social Media, Soundings, Email
| Invited Speaker Abstract Fees | Upon opening abstract submission process | Program Chair | *If Program Chair set aside PCF to waive abstract fees for invited speakers, he/she should provide AMS staff with a list of those speakers *AMS Staff will instruct Program Chair on process for invited speakers to submit abstract without paying the abstract fees (if covered by PCF)
| Advertise Student Opportunities | 2 months prior to abstract deadline | AMS Staff | *AMS Staff sends info on student opportunities for inclusion in AMS Chapter Newsletter *AMS Staff sends email to marketing mailing list about student opportunities | AMS Chapter Newsletter, Social Media, Email
| First Abstract Submission Reminder | 1 month prior to abstract deadline | AMS Staff | *AMS Staff sends reminder that the abstract submission deadline is approaching | Social Media, Soundings, Email
| Send Program Chair Tips | 2 weeks prior to abstract deadline | AMS Staff | *AMS Staff sends Program Chair Tips, which will provide a basic outline for program scheduling and explain how to use Confex (online abstract system) to organize the program *This email will also include a link an instructions to access the Program in Confex. Program Chairs can access and view the abstracts and the program, but should not make any changes until the abstract deadline has passed *If Program Chair wishes, AMS Staff can set up an online tutorial with Confex *Tips should also include an outline of the meeting space contracted so that Program Chair and Committee can work within those contraints
| Second Abstract Submission Reminder | 1 week prior to abstract deadline | AMS Staff | *AMS Staff sends another reminder that the abstract submission deadline is approaching | Social Media, Soundings, Email
| Abstract Deadline | 4 months prior to meeting | Abstract Authors | *This deadline can be extended (customarily AMS extends 1 week) but other deadlines will not be adjusted based on extension.
| Abstract Deadline Extension | 1-2 weeks after abstract deadline | Abstract Authors |  | Social Media, Soundings, Email
| Abstract Selection and Program Organization | upon abstract deadline | Program Chair and Program Committee | *Program Chair and Committee log into Confex to review submitted abstracts and schedule them (all organization must take place using the online system) *Based on prior requests and time constraints, Program Chair and Committee will discuss possible speical events, poster sessions, keynotes etc.
| Staff Travel Arrangements are Made/Fill Out Podium Setup | 1 week before program is finalized | AMS Staff | *AMS Staff makes hotel reservations for AMS Staff, AMS Vendors, and AMS Student Travel Grant Winners *AMS Staff should also book travel at this time
| Sponsorship Commitment Deadline | 1 week before program is finalized | Sponsors | *While we would accept sponsorships until the start of the meeting, this is the last day for sponsorship commitment to offset/lower registration costs
| Finalization of Program and Special Events | 1 month after the abstract deadline | Program Chair and Program Committee | *Program will be turned back over to AMS Staff (Program Chair and Committee will no longer have access to the organizing portion of Confex) *Based on prior requests and special events included in the Final Program turned over by Program Chair and Committee, AMS Staff will determine/discuss changes to the base registration rate for the meeting (registration rates are subject to increase if events were not included in the original budget for the meeting)
| Final Program Committee Members | 1 month after the abstract deadline | Program Chair | *Program AMS staff with the final list of the program committee to be included on the online program and the printed program.
| Open Registration Process | 1 month after the abstract deadline | AMS Staff | *Upon approval of rates from the Program Chair, AMS Staff will open the online registration system and post .pdf registration forms to the web for meeting and short course (if applicable) | Social Media, Soundings, Email
| Update Meeting Webpage | 1 month after the abstract deadline | AMS Staff | *AMS Staff updated Webpage (hotel information, registration rates, travel information, special events and food functions, presenter/poster information, exhibit information, and short course information)
| Post Program to Webpage | 1 month after the abstract deadline | AMS Staff | *AMS Staff cleans up the online program and posts to the Meeting Webpage | Social Media, AMS Meetings Homepage, Soundings, Email
| Send Abstract Acceptance Emails | 1 month after the abstract deadline | AMS Staff and Program Chair | *AMS Staff sends abstract acceptance emails to authors, along with links to Meeting Webpage *AMS Staff prepares and sends invoices for any unpaid abstract fees *Program Chair should confirm list of invited speaker abstract fees that will be covered by PCF so that invited speakers are not billed
| Send Student Opportunities to Student Presenters | After acceptance emails are sent | AMS Staff | *AMS Staff emails all student presenters information about the student opportunities available at the meeting
| Prepare for Student Award Competition and Student Travel Allowance | After acceptance emails are sent | AMS Staff and Program Chair | *AMS Staff sends Program Chair a preliminary list of student award candidates (will be updated 2 weeks before meeting), Student Award Judging Example, Student Award Prog Chair Email Example, and Notification Email Example *Program chair should enlist judges and organize them *If Program Chair has allotted PCF for Student Travel Allowance, he/she should contact those recipients and copy AMS Staff (who will then contact recipients regarding distribution of travel allowance) *If PCF have been alloted for Student Travel Allowance and Chair has not received any application/candidates, AMS Staff can email student presenters
| Prepare Exhibit Service Manual | 3 months prior to meeting | AMS Staff | *AMS Staff prepares and posts Exhibit Service Manual to exhibitors (includes floor plans, contractor information, registration forms, and housing/general information)
| Finalize Session Chairs | 2-3 months prior to meeting | Program Chair | *If not already entered into Confex during program development (recommended), Program Chair should send a list of session chairs to AMS Staff
| Process Pre-Registrations | 2 months prior to meeting | AMS Staff | *AMS Staff enters all registration forms received via fax/mail and sends receipts
| Schedule On-Site Committee Meeting | 2 months prior to meeting | AMS Staff | *AMS Staff asks Program Chair if there will be a Committee Meeting during the Meeting - if so, which day and whether it will be a breakfast, luncheon, or dinner *If Meeting is desired, AMS Staff will contact Program Committee and coordinate RSVPs and meal requests
| Finalize Venue and Conference Agenda | 2 months prior to meeting | AMS Staff | *AMS Staff selects menus for food events *AMS Staff sends final food and beverage requirements to venue *AMS Staff orders all necessary audiovisual Equipment
| AMS Student Travel Grant Application Deadline | 1.5-2 months prior to meeting | AMS Staff (Development) Program Chair | *Program chair will be contracted by AMS after application deadline to select AMS Student Travel Grant Winner(s). These grants are separate from awards given with Program Chair Funds.
| Enlist Student Volunteers | 6 weeks prior to meeting | AMS Staff | *While student volunteers are accepted from when the meeting webpage is developed, if volunteers are still needed, AMS staff will email all student presenters about volunteer opportunity
| Exhibitor Mailing | 1-2 months prior to meeting | AMS Staff | *AMS Staff to send out final mailing to exhibiting companies
| Pre-Registration (Early Bird) Deadline Reminder | 1 week before Pre-Registration Deadline | AMS Staff | *AMS Staff sends out reminder to register at the lowest rates | Social Media, AMS Meetings Homepage, Soundings, Email
| Hotel Reservation Deadline Reminder | 1 week before Hotel Reservation Deadline | AMS Staff | *AMS Staff sends out reminder to make hotel reservations | Social Media, AMS Meetings Homepage, Soundings, Email
| Pre-Registration (Early Bird) Deadline | 1-2 months prior to meeting | Attendees | *This is the last day attendees may register at the lowest registration rates
| Hotel Reservation Deadline | 1-2 months prior to meeting | Attendees | *This deadline depends on the hotel contract. Advertised deadline should be 5-7 days before actual deadline and advertised deadline should match pre-registration deadline if possible.
| Contact Session Chairs | 1-2 months prior to meeting | AMS Staff and Program Chair | *Program Chair, with AMS Staff develops and information email for session chairs (roles/responsibilities, confirm presenters will attend) *AMS sends out email to session chairs on behalf of program chair, includes list of presenters by session
| Confirm Student Award Candidates | 1 month prior to meeting | AMS Staff | *AMS Staff emails all presenters with a list of those currently on the list of Student Award Candidates, asks them to identify themselves if they should be on the list and they are not
| Meeting in Soundings Calendar | 1 month prior to meeting | AMS Staff | *AMS Staff provides meeting info and link for Soundings Calendar | Soundings
| Send Author Information Emails | 1 month prior to meeting | AMS Staff | *AMS Staff prepares and sends informational emails to Oral and Poster Presenters (includes poster numbers) *Includes reminder for changes to title/author info in program
| Signs and Poster Requirements | 1 month prior to meeting | AMS Staff | *AMS Staff coordinates all signage and poster boards needs with decorating company
| Organize Student Volunteers | 1 month prior to meeting | AMS Staff | *With students, AMS Staff develops a student volunteer schedule *AMS Staff requests stipen money from AMS accounting for distribution at the conclusion of the meeting
| Last Day for Edits to Abstract Titles and Author Information | 3 weeks prior to shipment date | Authors | *This is the last day that authors will be able to edit their abstract titles and author lists in Presenter's Corner *Any edits needed after this day will have to be made by AMS Staff
| Pull/Lay Out Technical Program and Author Index | 2 weeks prior to shipment date | AMS Staff | *AMS Staff pulls technical program, author index, and daily grids from Confex and lays them out. Any changes made to the technical program after this day will be included in the onsite addendum
| Prepare Program Foreword | 1 week prior to Program goes to press | Program Chair | *AMS Staff will provide program chair with template or past meeting's foreword
| Send Updated List of Student Award Candidates | 2 weeks before meeting | AMS Staff | *AMS Staff sends Program Chair updated list of student award candidates for judging
| Last day to Register byFax/Mail | 1 week prior to shipment date | Attendees | *Last day for attendees to register via fax in or mailed form. After this day, AMS Staff will print, proof and include all badges in shipment to conference venue
| Benefits of Sponsorship are Set Up | 1 week prior to shipment date | AMS Staff | *Logo posted on webpage; logo included in program; logo included on signage; confirmation of sponsor mention in opening/closing remarks; comp registration for one representative
| Program Goes to Press | 1 week prior to shipment date | AMS Staff | *AMS Staff puts all program files (Cover, Foreword, Conference Series, General Information, Technical Program, Daily Grids, Author Index, Exhibit Info (where applicable), and Venue Map) together and sends to press
| Ship Materials to Conference Venue | 1 week to 10 days prior to meeting | AMS Staff | *AMS Staff prepares shipment from HQ to meeting *This shipment includes programs, badges, poster numbers, and all registration and office materials needed for the meeting
| Presentation Upload Deadline | 1 week to 10 days prior to meeting | Confex | *This is the last day that presenters can upload their presentation slides to Presenter's Corner before the meeting. Those who do not upload by this deadline will have to upload their slides on site.
| Student Volunteer Confirmation | 1 week prior to meeting | AMS Staff | *AMS Staff recirculates student volunteer schedule and confirms that students will arrive for training *If a student does not confirm, AMS Staff will reach out to those on the waiting list
| See You Soon Marketing | 1 week prior to Meeting | AMS Staff | *AMS Staff reaches out to highlight special events and sessions and meeting location to drum up interest in meeting | Social Media, Email
| Pre-Conference Meeting | 1 day prior to meeting | AMS Staff | *AMS meets with hotel staff to discuss event and finalize any last minute details
| On Site Addendum | each day of meeting | AMS Staff | *AMS Staff will prepare and print an updated onsite addendum each day and post at registration as well at the head table of each session room
| Meeting Kickoff | First day of meeting | AMS Staff | *AMS Staff takes photo of first day to post on Social Media | Social Media
| On Site Meeting Details | at meeting | AMS Staff | *AMS Staff to process all registrations and act as liason with all Hotel Staff
| Special Event Highlight | at meeting | AMS Staff | *AMS Staff takes photo of special event to post on Social Media | Social Media
| Plan for Next Meeting | at meeting | Program Chair and Program Committee | *During Committee Meeting, Program Chair and Program Committee discuss current meeting and being planning for next meeting (AMS Staff member will be present)
| Determine Student Award Winners | at meeting | Program Chair and Program Committee | *Program Chair and Program Committee select student award winners (if applicable)
| Last Day to Register Online | Last Day of meeting | Attendees
| Thanks for Attending | Last Day of meeting | AMS Staff | *AMS Staff takes photo of last day to thank attendees | Social Media
| Meeting Added to Past Meetings Webpage | 1 week after meeting | AMS Staff | *AMS Staff creates a listing for the meeting on the AMS Past Meetings Webpage (Includes Program, Student Awards, Exhibitor Listing and link to archived Meetings Webpage)
| Student Award Winner Notification and Award Distribution | 1 week after meeting | AMS Staff, Program Chair, and Program Committee | *Program Chair notifies student award winners (copies AMS staff) *AMS Staff sends certificates/monetary prizes (if applicable) *AMS Staff collects receipts for student travel allowance and sends checks
| Meeting Survey | 1 week after meeting | AMS Staff, Current Program Chair, and Future Program Chair | *AMS Staff sends Current and Future Program Chair a template for the meeting survey and survey cover letter *Current and Future Program Chairs edit survey and cover letter and return to AMS Staff within 1 week *AMS Staff sends to meeting attendees
| Meeting Financial Clean-Up | 1 week after meeting | AMS Staff | *AMS Staff sends invoices for any unpaid registrations *AMS Staff arranges for payment of student volunteer stipends if not distributed on-site *AMS Staff pays all necessary vendors *AMS Staff updates budget with actuals
| Meetings Recap | 2 weeks after Meeting | Program Chair | *Program Chair provides AMS Staff with a Meeting Recap
| Meeting Survey Reminder | 2 weeks after Meeting | AMS Staf | *AMS Staff sends reminder to meeting attendees for survey
| Supplementary Info Upload Deadline Reminder | 3 weeks after Meeting | AMS Staff | *AMS Staff sends email to all presenters to remind them to upload supplementary info
| Supplementary Info Upload Deadline | 1 month after meeting | AMS Staff | *Last day for authors to upload Extended Abstracts, Poster Images, Optional PDFs and enter urls in Presenter's Corner
| Post Meeting Announcement | 1 month after meeting | AMS Staff | *AMS Staff to announce availability of Recordings, Supplementary Info, Meetings Recap, Student Awards | Social Media, Soundings, Email, BAMS, Meetings Webpage
| Survey Results | 1 Month after meeting | AMS Staff | *AMS Staff circulates survey results to Current and Future Program Chair and Committee