## Sheet1
Task | When to Initiate Task | Party Responsible | Task Description | Deadline
Select Program Chairperson | 1.5-2 years prior to meeting | AMS Board or Committee | *Program Chair is selected, appointed, or volunteers; (Selection usually takes place at previous conference during Board/Committee meeting)
Select Program Committee | 1.5-2 years prior to meeting | Program Chair | *Program Chair selects those who will help organize the program
Select Meeting Location (City, State) | 1.5-2 years prior to meeting | Program Chair and AMS Staff | *Program chair and committee discuss and provide 3 ranked locations and dates for meeting *AMS Staff researches options and reports back to program chair *AMS Staff, Program Chair, and Program Committee select a final location based on dates, room rates, facility availability etc. *Program Chair and Program Committee completes and returns Meeting Space and Program Requirements Worksheet (Parallel Sessions, Poster Session Size, Banquet, Food at Breaks, Exhibits, Short Course, Sponsorship, AV Needs)
Select Meeting Location (Hotel/Dates) | 1-1.5 years prior to meeting | Program Chair and AMS Staff | *AMS Staff gathers proposals from appropriate hotels in the chosen meeting city *AMS Staff and Program Chair discuss proposals and select a hotel based on available dates, room rates, and room requirements *AMS staff negotiates and signs hotel contract
Develop Meeting Budget | 1-1.5 years prior to meeting | AMS Staff | *Using Meeting Space and Program Requirements Worksheet, AMS Staff develops budget for all aspects of the meeting
Develop Meeting Theme | 1-1.5 years prior to meeting | Program Chair and Program Committee | *Program Chair and Committee develops a conference theme and/or special subject matter to incorporate into Call of Papers (if applicable)
Develop Exhibits Program | 1-1.5 years prior to meeting | AMS Staff, Program Chair, and Program Committee | *Develop exhibit program (if applicable) *Discuss and develop preliminary exhibit schedule *Program Committee to provide AMS Staff with list of possible exhibitors *AMS Staff develops floor plan *AMS Staff starts developing service manual and marketing plan
Develop Short Course Program | 1-1.5 years prior to meeting | AMS Staff and Program Chair | *Develop short course (if applicable) *Program Chair reaches out to potential short course organizers *Short Course organizer submuts application for course to Board of Continuing Education for approval
Seek Sponsorship | 1-1.5 years prior to meeting | AMS Staff, and Program Chair | *AMS Staff develops a list of possible items to be sponsored *Program Chair provides list of potential sponsors to AMS Staff *AMS Staff reaches out to potential sponsors
Discuss Local Chapter Involvement | 1-1.5 years prior to meeting | AMS Staff and Program Chair | *AMS Staff and Program Chair discuss possibility of involving the Local AMS Chapter in the meeting *AMS Staff to Local Chapter President to consider collaboration if desired
Discuss Program Chair Responsibilities and Deadlines | 1-1.5 years prior to meeting | AMS Staff and Program Chair | *AMS Staff contacts Program Chair with Meeting Deadlines (THIS Document) and discusses tasks *AMS Staff explains availability/approval process for Program Chair Funds (Program Chair submits FOrm for approval by STAC Chair)
Develop Meeting Deadlines | 1-1.5 years prior to meeting | AMS Staff | *AMS Staff determines Abstract and Meeting Deadlines *AMS Staff Requests Call for Papers and Session Topics
Prepare and Publish Call for Papers | 1 year prior to meeting | Program Chair and Program Committee | *AMS Staff provides Program Chair with skeleton for Call for Papers, as well as deadline dates *Program Chair develops Call for Papers (includes meeting sheme, session and abstract topics, abstract deadlines, joint sessions, and student contests) and submits to AMS Staff *AMS Staff publishes Call for Papers on AMS website and in BAMS
Open Abstract Submission Process and Develop Meeting Webpage | 10-12 months prior to meeting | AMS Staff | *AMS Staff opens online abstract submission process *AMS Staff Emails past meeting authors and attendees soliciting abstract submissions *AMS Staff develops and sets up Meeting Webpage on AMS website (meeting dealines, hotel information, author instructions, exhibits (if applicable))
Send Program Chair Tips | 2 weeks prior to abstract deadline | AMS Staff | *AMS Staff sends Program Chair Tips, which will provide a basic outline for program scheduling and explain how to use Confex (online abstract system) to organize the program *If Program Chair wishes, AMS Staff can set up an online tutorial with Confex
Abstract Deadline | 4 months prior to meeting
Abstract Selection and Program Organization | upon abstract deadline | Program Chair and Program Committee | *Program Chair and Committee log into Confex to review submitted abstracts and schedule them (all organization must take place using the online system) *Based on prior requests and time constraints, Program Chair and Committee will discuss possible speical events, poster sessions, keynotes etc.
Finalization of Program and Special Events | 1 month after the abstract deadline | Program Chair and Program Committee | *Program will be turned back over to AMS Staff (Program Chair and Committee will no longer have access to the organizing portion of Confex) *Based on prior requests and special events included in the Final Program turned over by Program Chair and Committee, AMS Staff will determine/discuss changes to the base registration rate for the meeting (registration rates are subject to increase if events were not included in the original budget for the meeting)
Open Registration Process | 1 month after the abstract deadline | AMS Staff | *Upon approval of rates from the Program Chair, AMS Staff will open the online registration system and post .pdf registration forms to the web for meeting and short course (if applicable)
Post/Publish General Information | 1 month after the abstract deadline | AMS Staff | *AMS Staff develops General Information (hotel information, registration rates, travel information, special events and food functions, poster information, exhibit information, and short course information) * AMS posts General Inforamtion on the Meeting Webpage and sends to publication in BAMS
Post Program to Webpage | 1 month after the abstract deadline | AMS Staff | *AMS Staff cleans up the online program and posts to the Meeting Webpage
Send Abstract Acceptance Emails | 1 month after the abstract deadline | AMS Staff | *AMS Staff sends abstract acceptance emails to authors, along with links to Meeting Webpage (general information, program, registratration) *AMS Staff prepares and sends invoices for any unpaid abstract fees
Prepare Exhibit Service Manual | 3 months prior to meeting | AMS Staff | *AMS Staff prepares and posts Exhibit Service Manual to exhibitors (includes floor plans, contractor information, registration forms, and housing/general information)
Process Pre-Registrations | 2 months prior to meeting | AMS Staff | *AMS Staff enters all registration forms received via fax/mail and sends receipts
Schedule On-Site Committee Meeting | 2 months prior to meeting | AMS Staff | *AMS Staff asks Program Chair if there will be a Committee Meeting during the Meeting - if so, which day and whether it will be a breakfast, luncheon, or dinner *If Meeting is desired, AMS Staff will contact Program Committee and coordinate RSVPs and meal requests
Finalize Hotel and Conference Agenda | 2 months prior to meeting | AMS Staff | *AMS to determine staffing needs and make necessary Hotel/Travel arrangements for staff and student travel grant winners *AMS Staff selects menus for food events *AMS Staff sends final food and feverage requirements to hotel *AMS Staff orders all necessary Audiovisual Equipment
Exhibitor Mailing | 1-2 months prior to meeting | AMS Staff | *AMS Staff to send out final mailing to exhibiting companies
Send Pre-Registration and Hotel Deadline Reminder Emails | 1-2 months prior to meeting | AMS Staff | *AMS Staff sends emails to authors, reminding them of the pre-registration and hotel reservation deadlines
Enlist/Organize Sutdent Volunteers | 1-2 months prior to meeting | AMS Staff | *AMS Staff emails student authors regarding the opportunity to volunteer at the meeting *With students, AMS Staff develops a student volunteer schedule
Send Author Information Emails | 1 month prior to meeting | AMS Staff | *AMS Staff prepares and sends informational emails to Oral and Poster Presenters
Signs and Poster Requirements | 1 month prior to meeting | AMS Staff | *AMS Staff coordinates all signage and poster boards needs with decorating company
Print Program/Prepare Shipment | 2-3 weeks prior to meeting | AMS Staff | *AMS Staff lays out program and sends to press *AMS Staff prepares shipment from HQ to meeting (shipment date is 1-1.5 weeks prior to meeting)
Contact Session Chairs | 2 weeks prior to meeting | AMS Staff and Program Chair | *Program Chair, with AMS Staff develops and information email for session chairs *AMS sends out email to session chairs
Pre-Conference Meeting | 1 day prior to meeting | AMS Staff | *AMS meets with hotel staff to discuss event and finalize any last minute details
On Site Meeting Details | at meeting | AMS Staff | *AMS Staff to process all registrations and act as liason with all Hotel Staff
Plan for Next Meeting | at meeting | Program Chair and Program Committee | *During Committee Meeting, Program Chair and Program Committee discuss current meeting and being planning for next meeting (AMS Staff member will be present)
Determine Student Award Winners | at meeting | Program Chair and Program Committee | *Program Chair and Program Committee select student award winners (if applicable) *Program Chair and Program Committee put together a short write up of results for publication in BAMS
Notify Student Award Winners/Publish Results | 1 week after meeting | AMS Staff | *AMS Staff to notify student award winners and send certificates/monetary prizes (if applicable) *AMS Staff to send write up on winners to BAMS for publication
Meeting Clean-Up | 1 week after meeting | AMS Staff | *AMS Staff sends invoices for any unpaid registrations *AMS Staff arranges for payment of student volunteer stipends if not distributed on-site *AMS Staff pays all necessary vendors